## Summary (hidden)
Summary of APP and RAPP 2022-23 of CEDP
| APP 2022-23 |  |  | RAPP 2022-23
| Total Packages for APP | Incomplete Packages | Complete Packages | New Packages | Total Packages for RAPP
GD | 34 | 19 | 15 | 6 | 21
SD | 35 | 10 | 25 | 0 | 25
WD | 7 | 4 | 3 | 1 | 4
Total | 76 | 33 | 43 | 7 | 50

## APP Goods 22-23 (hidden)
GOVERNMENT OF THE PEOPLE’S REPUBLIC OF BANGLADESH College Education Development Project (CEDP) Secondary and Higher Education Division, Ministry of Education Annual Procurement Plan of Goods for FY 2022-2023
Serial | Contract Package No. | Description of Procurement Package as per DPP GOODS | Unit | Qty /nos | Procurement Method/ Type | Contract Approving Authority | Source of Fund | Estimated Costs (In lakh taka) | Indicated Dates | [5 empty] | Total Time for Contract Signature | Time for Completion of Contract
[9 empty] | Advertise Tender | Tender Openining | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract
1 | GD101I | Computer & Accessories | nos | 8 | RFQ | Project Director | GoB | 5 | 2022-08-15 | 2022-08-25 | 2022-08-25 | 2022-09-01 | 2022-09-08 | 0 |  | 2022-09-28
2 | GD 102B | Motor Vehicles | nos | 1 | DPM | Vice Chancellor | GoB | 95 | 2022-09-15 | 2022-10-06 | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-12-01 |  | 2022-12-31
3 | GD103H | Procurement of Wheels and Other accessories for Vehicles of CEDP | nos | 24 | RFQ | Project Director | IDA | 5 | 2022-09-15 | 2022-09-25 | 2022-09-25 | 2022-10-02 | 2022-10-09 | 0 |  | 2022-10-29 | Done
4 | GD 105D | Procurement of Photocopier, Scanner, IPS and other Accessories for PMU office | nos | 15 | RFQ | Project Director | GoB | 5 | 2022-10-15 | 2022-10-25 | 2022-10-25 | 2022-11-01 | 2022-11-08 | 0 |  | 2022-11-28
5 | GD105B | Interactive Smart Virtual Class Room/ E-learning Centre for NAEM, NU & BOU | nos | 25 | OTM | Minister, MOE | GoB | 2860 | 2022-08-15 | 2022-09-12 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-11-14 |  | 2023-06-27
6 | GD 105C | Installation of IP Telephony System & Networking for PMU office | nos | 45 | RFQ | Project Director | GoB | 5 | 2022-11-15 | 2022-11-25 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 0 |  | 2022-12-29 | Done
7 | GD106B | Laboratory Instrument and Accessories under Training Facilities (NU) | nos | 2 | OTM | Vice Chancellor | GoB | 100 | 2022-08-25 | 2022-09-08 | 2022-09-29 | 2022-10-06 | 2022-10-13 | 2022-11-10 |  | 2023-06-23
8 | GD106F | Laboratory Instrument and Accessories under Training Facilities (NU) | nos | 4 | OTM | Vice Chancellor | GoB | 200 | 2022-09-25 | 2022-10-09 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-12-11 |  | 2023-06-27
9 | GD106H | Procurement of printer, projector and Accessories under Training Facilities (NU) | nos | 64 | OTM | Vice Chancellor | GoB | 50 | 2022-08-25 | 2022-09-08 | 2022-09-29 | 2022-10-06 | 2022-10-13 | 2022-11-10 |  | 2023-06-08
10 | GD106I | Tab with Apps under Training Facilities (NU) (Re-Tender) | nos | 2400 | OTM (e-GP) | Vice Chancellor | GoB | 597.65 | 2022-03-21 | 2022-04-07 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-06-13 |  | 2022-08-12
11 | GD106J | Development of Conference Room under Training Facilities (NU) | nos | 1 | OTM | Vice Chancellor | GoB | 100 | 2022-08-15 | 2022-08-29 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-31 |  | 2023-05-29
12 | GD106K | Procurement of digital notice board and Accessories under Traning Facilities (NU) | nos | 5 | OTM | Vice Chancellor | GoB | 20 | 2022-07-20 | 2022-08-03 | 2022-08-24 | 2022-08-31 | 2022-09-07 | 2022-10-05 |  | 2023-05-03
13 | GD106L | Tab with Apps under Traning Facilities (NU) | nos | 1600 | OTM | Vice Chancellor | GoB | 400 | 2022-10-25 | 2022-11-08 | 2022-11-29 | 2022-12-06 | 2022-12-13 | 2023-01-10 |  | 2023-08-08
14 | GD106M | Procurement of interactive smart board, smart TV and Accessories for digital class room under Traning Facilities (NU) | NS | 7 | OTM | Vice Chancellor | GoB | 40 | 2022-10-25 | 2022-11-08 | 2022-11-29 | 2022-12-06 | 2022-12-13 | 2023-01-10 |  | 2023-06-29
15 | GD107B | Framework Agreement for Procurement of Stationery Items, Toner & Accessories and Bags | NS | LumpSum | OTM | Vice Chancellor | GoB | 81.23 | 2021-05-19 | 2021-06-10 | 2021-08-19 | 2021-08-24 | 2021-08-25 | 2021-09-09 |  | 2023-09-08
16 | GD 107C | Framework Agreement for Procurement of Stationeries Items, Toner & Accessories and Bags | NS | LumpSum | OTM | Vice Chancellor | GoB | 200 | 2022-09-25 | 2022-10-09 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-12-11 |  | 2023-12-31
17 | GD108C | Printing and Publications for PMU, CEDP | nos | 1500 | RFQ | Project Director | GoB | 5 | 2022-11-15 | 2022-11-25 | 2022-11-25 | 2022-12-02 | 2022-12-09 | 0 |  | 2022-12-29 | Done
18 | GD108D | Printing and Publications for PMU, CEDP | nos | 5000 | OTM | Vice Chancellor | GoB | 15 | 2022-12-15 | 2022-12-29 | 2023-01-19 | 2023-01-26 | 2023-02-02 | 2023-03-02 |  | 2023-06-30
19 | GD108F | Printing and Publications for PMU | nos | 1500 | RFQ | Project Director | GoB | 5 | 2022-11-25 | 2022-12-05 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 0 |  | 2023-01-08 | Done
20 | GD109A | Framework Agreement for Procurement of Books under Training Facilities (NU) | NS | LumpSum | OTM | Vice Chancellor | GoB | 92.8 | 2020-09-29 | 2020-10-19 | 2020-12-29 | 2021-01-02 | 2021-01-06 | 2021-02-03 |  | 2022-09-26
21 | GD 110 | Infrastructure Hardware & Software for LMS & Content | NS | LumpSum | OTM | Vice Chancellor | GoB | 300 | 2022-09-25 | 2022-10-23 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-25 |  | 2023-06-23
22 | GD-115B | Recruitment of Support Staffs (6 Drivers and 4 Office Assistants) for CEDP | NS | LumpSum | DPM | Vice Chancellor | GoB | 26.39 | - | - | - | 2022-01-11 | 2022-01-12 | 2022-01-31 |  | 2023-01-31
23 | GD-115C | Recruitment of Support Staffs (6 Drivers and 4 Office Assistants) for CEDP | NS | LumpSum | DPM | Vice Chancellor | GoB | 26 | 0 | 0 | 0 | 2023-01-11 | 2023-01-18 | 2023-01-31 |  | 2023-12-31
24 | IDG/CP/GD-04A | Supply of Digital Smart Board for Classroom & Related Services for IDG Colleges of Dhaka and Chittagong Division under CEDP (Re-Tender) | NS | LumpSum | OTM (e-Gp) | Vice Chancellor | GoB | 1326 | 2021-05-11 | 2021-05-31 | 2021-08-12 | 2021-08-17 | 2021-08-17 | 2021-09-08 |  | 2022-09-07
25 | IDG/CP/GD-04B | Supply of Digital Smart Board for Classroom & Related Services for IDG Colleges of Barishal Khulna Mymensingh Rajshahi Rangpur and Sylhet Division under CEDP (Re-Tender) | NS | LumpSum | OTM (e-Gp) | Vice Chancellor | GoB | 1398.18 | 2021-08-22 | 2021-09-14 | 2021-12-13 | 2021-12-19 | 2021-12-20 | 2021-12-28 |  | 2022-09-26
26 | IDG/CP/GD-05 | Supply of Digital Notice Board and Related Service for IDG Colleges under CEDP. (Re-Tender) | NS | LumpSum | OTM (e-Gp) | Vice Chancellor | GoB | 480 | 2022-07-20 | 2022-08-17 | 2022-09-07 | 2022-09-21 | 2022-09-28 | 2022-10-26 |  | 2023-04-24
27 | IDG/CP/GD-06A | Campus Networking for IDG Colleges under CEDP | NS | LumpSum | OTM (e-Gp) | Vice Chancellor | GoB | 500 | 2022-09-25 | 2022-10-23 | 2022-11-13 | 2022-11-27 | 2022-12-04 | 2023-01-01 |  | 2023-05-02
28 | IDG/CP/GD-06B | Campus Networking for IDG Colleges under CEDP | NS | LumpSum | OTM (e-Gp) | Vice Chancellor | GoB | 500 | 2022-10-25 | 2022-11-22 | 2022-12-13 | 2022-12-27 | 2023-01-03 | 2023-01-31 |  | 2023-06-01
29 | IDG/CP/GD-06C | Campus Networking for IDG Colleges under CEDP | NS | LumpSum | OTM (e-Gp) | Vice Chancellor | GoB | 500 | 2022-11-15 | 2022-12-13 | 2023-01-03 | 2023-01-17 | 2023-01-24 | 2023-02-21 |  | 2023-06-22
30 | IDG/CP/GD-06D | Campus Networking for IDG Colleges under CEDP | NS | LumpSum | OTM (e-Gp) | Vice Chancellor | GoB | 500 | 2022-11-20 | 2022-12-18 | 2023-01-08 | 2023-01-22 | 2023-01-29 | 2023-02-26 |  | 2023-06-27
31 | IDG/CP/GD-06E | Campus Networking for IDG Colleges under CEDP | NS | LumpSum | OTM (e-Gp) | Vice Chancellor | GoB | 500 | 2022-11-30 | 2022-12-28 | 2023-01-18 | 2023-02-01 | 2023-02-08 | 2023-03-08 |  | 2023-06-26
32 | IDG/CP/GD-08A | Supply of Desktop Computer and Related Services for IDG Colleges Under CEDP | Nos | 924 | OTM (e-GP) | Vice Chancellor | GoB | 800 | 2022-09-01 | 2022-09-29 | 2022-10-20 | 2022-11-03 | 2022-11-10 | 2022-12-08 |  | 2023-06-06
33 | IDG/CP/GD-08B | Supply of Laptop Computer and Related Services for IDG Colleges Under CEDP | Nos | 305 | OTM (e-GP) | Vice Chancellor | GoB | 300 | 2022-09-20 | 2022-10-18 | 2022-11-08 | 2022-11-22 | 2022-11-29 | 2022-12-27 |  | 2023-06-20
34 | IDG/CP/GD-08C | Supply of Digital Smartboard and Related Services for IDG Colleges Under CEDP | Nos | 152 | OTM (e-GP) | Vice Chancellor | GoB | 700 | 2022-09-30 | 2022-10-28 | 2022-11-18 | 2022-12-02 | 2022-12-09 | 2023-01-06 |  | 2023-06-30
| Total Value of Goods Procurement | [6 empty] | 12738.25
| GD108K | Printing and Publications for PMU, CEDP | nos | 1500 | RFQ | Project Director | GoB | 5 | 2023-04-10 | 2023-04-20 | 2023-04-20 | 2023-04-27 | 2023-05-04 | 0 |  | 2023-05-24 | New for revised APP
Formulas:
Tender Openining = [Indicated Dates]+10
Tender Evaluation = [Tender Openining]+0
Approval to Award = [Tender Evaluation]+7
Time for Completion of Contract = [Notification of Award]+20
Time for Completion of Contract = [Signing of Contract]+30
Signing of Contract = [Notification of Award]+28
Notification of Award = [Approval to Award]+7

## APP Services 22-23 (hidden)
GOVERNMENT OF THE PEOPLE’S REPUBLIC OF BANGLADESH College Education Development Project (CEDP) Secondary and Higher Education Division, Ministry of Education Annual Procurement Plan of Goods for FY 2022-2023
Serial | Contract Package No. | Description of Procurement Package as per DPP SERVICES | Unit | Qty /nos | Proc. Method/ Type | Contract Approving Authority | Source of Fund | Estimated Costs (In lakh taka) | Indicated Dates | [6 empty] | Time for Completion of Contract
[9 empty] | Invitation for EoI | Eval of EoIs | Negotiation/ Issue of RFP | Issue of NOA | Signing of Contract | Contract Start date | Completion of Contract
35 | SD101A | National Consultant (Individual) IDG Specialist-1 (3.1) | PM | 12 | IC (Limited) | Vice Chancellor | IDA | 102.94 | 2021-10-10 | 2021-10-24 | 2021-11-01 | 2021-11-03 | 2021-11-14 | 2021-11-15 | 2023-12-31
36 | SD 102D | National Consultant (Individual) Monitoring and Evaluation Specialist (3.1) | PM | 21 | IC (Limited) | Vice Chancellor | IDA | 69.99 | 2022-03-16 | 2022-03-28 | 2022-04-11 | 2022-04-24 | 2022-04-25 | 2022-04-25 | 2023-12-31
37 | SD 103C | National Consultant (Individual) Environment and Social Safeguard Specialist (3.1) | PM | 17 | IC (Single source) | Vice Chancellor | IDA | 49.44 | 2021-12-07 | 2021-12-12 | 2021-12-23 | 2021-12-26 | 2021-12-26 | 2021-12-26 | 2023-05-25
38 | SD 104C | National Consultant (Individual) Procurement Specialist-1 (3.1) | PM | 18 | IC (Limited) | Vice Chancellor | IDA | 87.46 | 2022-03-28 | 2022-03-30 | 2022-03-30 | 2022-04-20 | 2022-07-01 | 2022-07-01 | 2023-12-31
39 | SD 105B | National Consultant (Individual) Procurement Specialist-2 (3.1) | PM | 29 | IC (Limited) | Vice Chancellor | IDA | 81.8 | 2021-07-01 | 2021-07-05 | 2021-07-15 | 2021-07-18 | 2021-07-27 | 2021-08-01 | 2023-12-31
40 | SD 106C | National Consultant (Individual) Senior Procurement Specialist (3.1) | PM | 24 | IC (Limited) | Vice Chancellor | IDA | 115.52 | 2021-07-28 | 2021-08-08 | 2021-08-19 | 2021-09-15 | 2021-11-01 | 2021-11-01 | 2023-10-31
41 | SD 107A1 | National Consultant (Individual) Junior Procurement Specialist-1 (3.1) | PM | 23 | IC (Single source) | Vice Chancellor | IDA | 55.7 | 2022-01-11 | 2022-01-23 | 2022-01-23 | 2022-01-30 | 2022-02-07 | 2022-02-07 | 2023-12-31
42 | SD 108B | National Consultant (Individual) ICT Specialist (3.1) | PM | 24 | IC (Limited) | Vice Chancellor | IDA | 79.27 | 2021-02-10 | 2021-02-17 | 2021-03-01 | 2021-03-07 | 2021-03-19 | 2021-03-19 | 2023-03-18
43 | SD 108C | National Consultant (Individual) ICT Specialist (3.1) | PM | 10 | IC (Limited) | Vice Chancellor | IDA | 34 | 2023-02-10 | 2023-02-17 | 2023-03-01 | 2023-03-07 | 2023-03-19 | 2023-03-19 | 2023-12-31
44 | SD 109C | National Consultant (Individual) Training Coordination Specialist (3.1) | PM | 23 | IC (Open) | Vice Chancellor | IDA | 74.89 | 2021-11-09 | 2022-01-19 | 2022-01-23 | 2022-01-25 | 2022-01-26 | 2022-01-26 | 2023-12-25
45 | SD 110C | National Consultant (Individual) Financial Management Specialist (3.1) | PM | 22 | IC (Open) | Vice Chancellor | IDA | 69.25 | 2021-11-09 | 2021-12-28 | 2022-02-27 | 2022-02-28 | 2022-03-02 | 2022-03-02 | 2023-12-31
46 | SD 111C | National Consultant (Individual) Accounts Specialist (3.1) | PM | 26 | IC (Limited) | Vice Chancellor | IDA | 70.56 | 2021-09-21 | 2021-10-07 | 2021-10-17 | 2021-10-21 | 2021-10-24 | 2021-10-24 | 2023-12-23
47 | SD 119 | National Consultant (Individual) Strategic Plan Specialist - 2 (3.1) | PM | 6 | IC (Single Source) | Vice Chancellor | IDA | 13.98 | 2021-11-28 | 2021-12-12 | 2021-12-12 | 2022-01-04 | 2022-01-06 | 2022-01-09 | 2022-07-08
48 | SD 124A | National Consultant (Individual) Junior Finance & Accounts Specialist (3.1) | PM | 31 | IC (Limited) | Vice Chancellor | IDA | 68.77 | 2021-05-02 | 2021-05-09 | 2021-05-19 | 2021-05-23 | 2021-05-27 | 2021-06-01 | 2023-12-31
49 | SD 125 | National Consultant (Individual) Associate Network & IT Specialist (3.1) | PM | 21 | IC (Open) | Vice Chancellor | IDA | 48.79 | 2020-02-07 | 2022-03-09 | 2022-03-13 | 2022-03-16 | 2022-03-21 | 2022-03-21 | 2023-12-20
50 | SD 126 | National Consultant (Individual) Self-Assesmentt Specialist (3.1) | PM | 27 | IC (Limited) | Vice Chancellor | IDA | 73.13 | 2021-09-14 | 2021-09-22 | 2021-09-30 | 2021-10-05 | 2021-10-06 | 2021-10-06 | 2023-12-31
51 | SD 127 | National Consultant (Individual) Associate Strategic Plan Specialist-1 (3.1) | PM | 365 days | IC (Limited) | Vice Chancellor | IDA | 48.84 | 2021-11-24 | 2021-12-23 | 2022-01-27 | 2022-01-31 | 2022-02-07 | 2022-02-07 | 2023-12-31
52 | SD 302 | Mid Term Satisfaction Survery (Beneficiary)-2 | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 66.81 | 2022-01-04 | 2022-02-10 | 2022-02-17 | 2022-02-23 | 2022-02-24 | 2022-03-01 | 2022-08-31
53 | SD 303 | Audit Firm | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 24.54 | 2021-05-06 | 2021-06-15 | 2021-08-08 | 2021-08-16 | 2021-09-01 | 2021-09-01 | 2023-10-31
54 | SD 403A | Survey and Studies (Effectiveness and Situation Assessment of Teacher's Training) | NS | Lumpsum | QCBS | Vice Chancellor | IDA | 24.22 | 2021-04-06 | 2021-06-15 | 2021-12-08 | 2021-12-09 | 2021-12-13 | 2021-01-01 | 2022-06-09
55 | IDG/CP/ SD 601 | Planning, Design, Development, Deployment, Implementation, maintenance and Support Services of Integrated College Management Information System (CMIS) (SD-601) | NS | Lumpsum | QCBS | Vice Chancellor | GoB | 600 | 2022-03-07 | 2022-07-05 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-09-20 | 2023-12-31
56 | SD 504 | Selection of Online Training Consulting Firm for Subjent Based Training | NS | Lumpsum | QCBS | Vice Chancellor | GoB | 100 | 2021-10-10 | 2022-02-27 | 2022-03-03 | 2022-08-15 | 2022-08-22 | 2022-09-01 | 2023-09-01
57 | SD 603 | Design, Development, Implementation and Maintenance of Learning Management System (LMS) for National University, Bangladesh | NS | Lumpsum | QCBS | Vice Chancellor | GoB | 300 | 2022-03-08 | 2022-06-13 | 2022-08-31 | 2022-09-07 | 2022-09-14 | 2022-09-14 | 2023-12-31
58 | IDG/CP/ SD 604A | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-08-15 | 2022-09-12 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-11-14 | 2023-05-13
59 | IDG/CP/ SD 604B | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-08-25 | 2022-09-22 | 2022-10-13 | 2022-10-20 | 2022-10-27 | 2022-11-24 | 2023-05-23
60 | IDG/CP/ SD 604C | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-09-01 | 2022-09-29 | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-12-01 | 2023-05-30
61 | IDG/CP/ SD 604D | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-09-15 | 2022-10-13 | 2022-11-03 | 2022-11-10 | 2022-11-17 | 2022-12-15 | 2023-06-13
62 | IDG/CP/ SD 604E | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-09-30 | 2022-10-28 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-30 | 2023-06-28
63 | SD 107B1 | National Consultant (Individual) Junior Procurement Specialist-2 (3.1) | PM | 17 | IC (Limited) | Vice Chancellor | IDA | 39.1 | 2022-09-01 | 2022-09-15 | 2022-10-06 | 2022-10-13 | 2022-10-20 | 2022-11-17 | 2023-12-31
64 | SD 123 | National Consultant (Individual) Communication & Mobilisation Specialist (3.1) | PM | 17 | IC (Limited) | Vice Chancellor | IDA | 48.45 | 2022-11-01 | 2022-11-15 | 2022-12-06 | 2022-12-13 | 2022-12-20 | 2023-01-17 | 2023-12-31
65 | SD 304 | LMS Content Development (Firm) | NS | Lumpsum | FBS | Vice Chancellor | GoB | 400 | 2022-09-01 | 2022-09-15 | 2022-10-15 | 2022-12-14 | 2022-12-21 | 2022-12-21 | 2023-12-31
66 | SD 401 | DLI Verification Consultancy Firm for DLI-4 (2nd round) | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 70 | 2022-09-01 | 2022-09-15 | 2022-10-15 | 2022-12-14 | 2022-12-21 | 2022-12-21 | 2023-06-30
67 | SD 403C | Survey and Studies (Effectiveness of the project) | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 70 | 2022-10-01 | 2022-10-15 | 2022-11-14 | 2023-01-13 | 2023-01-20 | 2023-01-20 | 2023-06-30
68 | SD 404 | Survey and Studies (Tracer Study-2) (Follow up Tracer Study on Graduates of Tertiary- Level Colleges) | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 70 | 2022-09-01 | 2022-09-15 | 2022-10-15 | 2022-12-14 | 2022-12-21 | 2022-12-21 | 2023-06-30
69 | SD 502 | Survey and Studies (Beneficiary-3: Endline Satisfaction Survey) | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 70 | 2022-10-01 | 2022-10-15 | 2022-11-14 | 2023-01-13 | 2023-01-20 | 2023-01-20 | 2023-06-30
| Total Value of Services Procurement | [6 empty] | 6527.45
Formulas:
Issue of NOA = [Negotiation/ Issue of RFP]+7
Contract Start date = [Signing of Contract]
Contract Start date = [Signing of Contract]+3
Negotiation/ Issue of RFP = [Eval of EoIs]+60
Completion of Contract = [Contract Start date]+365
Completion of Contract = [Contract Start date]+360+15
Signing of Contract = [Issue of NOA]+7
Eval of EoIs = [Indicated Dates]+28

## APP Works 22-23 (hidden)
GOVERNMENT OF THE PEOPLE’S REPUBLIC OF BANGLADESH College Education Development Project (CEDP) Secondary and Higher Education Division, Ministry of Education Annual Procurement Plan of Goods for FY 2022-2023
Serial | Contract Package No. | Description of Procurement Package as per DPP WORKS | Unit | Qty /nos | Procurement Method/ Type | Contract Approving Authority | Source of Fund | Estimated Costs (In lakh taka) | Indicative/Actual Dates | [5 empty] | Total Time for Contract Signature | Time for Completion of Contract
[9 empty] | Advertise Tender | Tender Openining | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract
70 | W-104 | Refurbishment Works of Dormitory Building at National University, Gazipur | NS | Lumpsum | OTM (e-GP) | Vice Chancellor | GoB | 177.24 | 2020-12-09 | 2020-12-24 | 2020-03-21 | 2021-03-24 | 2021-03-25 | 2021-04-13 | 125 | 2022-10-07
71 | W-101H | Interior Design Firm | NS | Lumpsum | RFQ | Project Director | GoB | 10 | 2022-10-20 | 2022-10-30 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 |  | 2022-12-03
72 | W-101I | Furniture and Fixtures, Interior | NS | Lumpsum | RFQ | Project Director | GoB | 10 | 2022-11-20 | 2022-11-30 | 2022-11-30 | 2022-12-07 | 2022-12-14 | 2022-12-21 |  | 2023-01-03
73 | NS-105D | Procurement of Physical Services from Service Provider Firm for Hiring Vehicles and Maintaining Transport Facilities | NS | LumpSum | OTM | Vice Chancellor | GoB | 195 | 2022-10-30 | 2022-11-13 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2023-01-15 |  | 2023-08-13 | RFQ 5 lac instead of OTM
74 | W-106A | Repair & Maintenance of Training Facilities | NS | LumpSum | RFQ | Project Director | GoB | 10 | 2022-12-30 | 2023-01-09 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 |  | 2023-02-12
75 | CEDP/NCS-01 | Training Program on "Best Practices of Project Cycle Management" at Istanbul University in Turkey | NS | Lumpsum | DPM | Vice Chancellor | IDA | 110.02 | 2022-02-13 | 2022-02-27 | 2022-02-27 | 2022-02-27 | 2022-02-28 | 2022-02-28 |  | 2022-12-30
76 | CEDP/NCS-02 | Servicing of Vehicles for PMU, CEDP | NS | Lumpsum | DPM | Vice Chancellor | IDA | 5 | 2022-09-15 | 2022-10-06 | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-12-01 |  | 2023-01-30
| Total Value of Works Procurement | [6 empty] | 517.26
| NS-105D1 | Procurement of Physical Services from Service Provider Firm for Hiring Vehicles and Maintaining Transport Facilities | NS | LumpSum | RFQ | Vice Chancellor | GoB | 5 | 2022-04-12 | 2022-04-17 | 2022-04-17 | 2022-04-20 | 2022-04-27 | 2022-05-04 |  | 2022-09-01 | Done As RFQ
Formulas:
Tender Openining = [Indicative/Actual Dates]+10
Tender Evaluation = [Tender Openining]+0
Approval to Award = [Tender Evaluation]+7
Time for Completion of Contract = [Notification of Award]+20
Time for Completion of Contract = [Signing of Contract]+210
Notification of Award = [Approval to Award]+7
Signing of Contract = [Notification of Award]+28

## APP Goods
GOVERNMENT OF THE PEOPLE’S REPUBLIC OF BANGLADESH Name of Procuring Entity Office Secondary and Higher Education Division, Ministry of Education Annual Procurement Plan of Goods
Serial | Contract Package No. | Description of Procurement Package as per DPP GOODS | Unit | Qty/ Nos | Procurement Method/ Type | Contract Approving Authority | Source of Fund | Estimated Costs (In lakh taka) | Indicated Dates | [5 empty] | Time for Completion of Contract | GOODS | Total Cost (In Lac) | Total Cost | Payments | [5 empty] | Remaining Cost | Remaining Cost (In Lac)
[9 empty] | Advertise Tender | Tender Openining | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract |  | Contract Package No. |  |  | 1st Bill/ 19-20 | 2nd Bill/ 20-21 | 3rd Bill/ 21-22 | 4th Bill/ 22-23 | 5th Bill/ 23-24 | Total Paid
1 |  |  | NS | LS | OTM (e-Gp) | Vice Chancellor | IDA/GoB |  | 2024-07-25 | 2024-08-04 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-29 | 2024-11-28 | 0 | 50 | 5000000 | [5 empty] | 0 | 5000000 | 50
2 |  |  | Nos |  | RFQ | Vice Chancellor | IDA/GoB |  | 2024-10-15 | 2024-10-25 | 2024-10-25 | 2024-11-01 | 2024-11-08 | 0 | 2024-11-28 | 0 | 5 | 500000 | [5 empty] | 0 | 500000 | 5
| Total Value of Goods Procurement | [6 empty] | 0 | [7 empty] | Total | 55 | 5500000 | [5 empty] | 0 | 5500000 | 55

## APP Services
GOVERNMENT OF THE PEOPLE’S REPUBLIC OF BANGLADESH Name of Procuring Entity Office: Secondary and Higher Education Division, Ministry of Education Annual Procurement Plan of Service
Serial | Contract Package No. | Description of Procurement Package as per DPP SERVICES | Unit | Qty/ Nos | Procurement Method/ Type | Contract Approving Authority | Source of Fund | Estimated Costs (In lakh taka) | Indicated Dates | [6 empty] | SERVICES | Total Cost (In Lac) | Total Cost | Payments | [5 empty] | Remaining Cost | Remaining Cost (In Lac)
[9 empty] | Invitation for EoI | Eval of EoIs | Negotiation/ Issue of RFP | Issue of NOA | Signing of Contract | Contract Start date | Completion of Contract | Contract Package No. |  |  | 1st Bill/ 19-20 | 2nd Bill/ 20-21 | 3rd Bill/ 21-22 | 4th Bill/ 22-23 | 5th Bill/ 23-24 | Total Paid
1 |  |  | PM |  | IC (Limited) | Vice Chancellor | IDA/GoB |  | 2024-10-10 | 2021-10-24 | 2021-11-01 | 2021-11-03 | 2021-11-14 | 2021-11-15 | 2023-12-31 | 0 | 102.94 | 10294000 |  |  | 2820912.3 | 4465491.43 |  | 7286403.73 | 3007596.27 | 30.076
2 |  |  | PM |  | IC (Limited) | Vice Chancellor | IDA/GoB |  | 2024-06-16 | 2022-03-28 | 2022-04-11 | 2022-04-24 | 2022-04-25 | 2022-04-25 | 2023-12-31 | 0 | 69.99 | 6999000 |  |  | 695500.01 | 3763694.13 |  | 4459194.14 | 2539805.86 | 25.3981
| Total Value of Services Procurement | [6 empty] | 0 | [7 empty] | Total | 172.93 | 17293000 | [5 empty] | 11745597.87 | 5547402.13 | 55.474

## APP Works
GOVERNMENT OF THE PEOPLE’S REPUBLIC OF BANGLADESH Name of Procuring Entity Office: Secondary and Higher Education Division, Ministry of Education Annual Procurement Plan of Works
Serial | Contract Package No. | Description of Procurement Package as per DPP WORKS | Unit | Qty/ Nos | Procurement Method/ Type | Contract Approving Authority | Source of Fund | Estimated Costs (In lakh taka) | Indicative/Actual Dates | [5 empty] | Time for Completion of Contract | WORKS | Total Cost (In Lac) | Total Cost | Payments | [5 empty] | Remaining Cost | Remaining Cost (In Lac)
[9 empty] | Advertise Tender | Tender Openining | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract |  | Contract Package No. |  |  | 1st Bill/ 19-20 | 2nd Bill/ 20-21 | 3rd Bill/ 21-22 | 4th Bill/ 22-23 | 5th Bill/ 23-24 | Total Paid
1 |  |  | NS | Lumpsum | OTM (e-GP) | Vice Chancellor | GoB |  | 2024-12-09 | 2020-12-24 | 2020-03-21 | 2021-03-24 | 2021-03-25 | 2021-04-13 | 2023-05-04 | 0 | 177.24 | 17724000 | 2009754 | 2409217 | 1693700 | 4283270 |  | 10395941 | 7328059 | 73.2806
2 |  |  | NS | LumpSum | RFQ | Vice Chancellor | GoB |  | 2024-06-04 | 2024-06-11 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2023-06-20 | 2023-07-20 | 0 | 4.87 | 487000 | [5 empty] | 0 | 487000 | 4.87
| Total Value of Works Procurement | [6 empty] | 0 | [7 empty] | Total | 182.11 | 18211000 | [5 empty] | 10395941 | 7815059 | 78.1506
|  |  |  | Goods |  |  |  | 0
|  |  |  | Service |  |  |  | 0
|  |  |  | Works |  |  |  | 0
[5 empty] | 0 | 0 | 0 | 0

## APP Servics 22_23 (hidden)
GOVERNMENT OF THE PEOPLE’S REPUBLIC OF BANGLADESH College Education Development Project (CEDP) Secondary and Higher Education Division, Ministry of Education Annual Procurement Plan of Service for FY 2022-2023
Contract Package No. | Description of Procurement Package as per DPP SERVICES | Unit | Qty /nos | Proc. Method/ Type | Contract Approving Authority | Source of Fund | Estimated Costs (In lakh taka) | Indicated Dates
[8 empty] | Invitation for EoI | Eval of EoIs | Negotiation/Issue of RFP | Issue of NOA | Signing of Contract | Contract Start date | Completion of Contract
SD101A | National Consultant (Individual) IDG Specialist-1 (3.1) | PM | 12 | IC (Limited) | Vice Chancellor | IDA | 102.94 | 2021-10-10 | 2021-10-24 | 2021-11-01 | 2021-11-03 | 2021-11-14 | 2021-11-15 | 2023-12-31
SD 102D | National Consultant (Individual) Monitoring and Evaluation Specialist (3.1) | PM | 21 | IC (Limited) | Vice Chancellor | IDA | 69.99 | 2022-03-16 | 2022-03-28 | 2022-04-11 | 2022-04-24 | 2022-04-25 | 2022-04-25 | 2023-12-31
SD 103C | National Consultant (Individual) Environment and Social Safeguard Specialist (3.1) | PM | 17 | IC (Single source) | Vice Chancellor | IDA | 49.44 | 2021-12-07 | 2021-12-12 | 2021-12-23 | 2021-12-26 | 2021-12-26 | 2021-12-26 | 2023-05-25
SD 104C | National Consultant (Individual) Procurement Specialist-1 (3.1) | PM | 18 | IC (Limited) | Vice Chancellor | IDA | 87.46 | 2022-03-28 | 2022-03-30 | 2022-03-30 | 2022-04-20 | 2022-07-01 | 2022-07-01 | 2023-12-31
SD 105B | National Consultant (Individual) Procurement Specialist-2 (3.1) | PM | 29 | IC (Limited) | Vice Chancellor | IDA | 81.8 | 2021-07-01 | 2021-07-05 | 2021-07-15 | 2021-07-18 | 2021-07-27 | 2021-08-01 | 2023-12-31
SD 106C | National Consultant (Individual) Senior Procurement Specialist (3.1) | PM | 24 | IC (Limited) | Vice Chancellor | IDA | 115.52 | 2021-07-28 | 2021-08-08 | 2021-08-19 | 2021-09-15 | 2021-11-01 | 2021-11-01 | 2023-10-31
SD 107A1 | National Consultant (Individual) Junior Procurement Specialist-1 (3.1) | PM | 23 | IC (Single source) | Vice Chancellor | IDA | 55.7 | 2022-01-11 | 2022-01-23 | 2022-01-23 | 2022-01-30 | 2022-02-07 | 2022-02-07 | 2023-12-31
SD 108B | National Consultant (Individual) ICT Specialist (3.1) | PM | 24 | IC (Limited) | Vice Chancellor | IDA | 79.27 | 2021-02-10 | 2021-02-17 | 2021-03-01 | 2021-03-07 | 2021-03-19 | 2021-03-19 | 2023-03-18
SD 108C | National Consultant (Individual) ICT Specialist (3.1) | PM | 10 | IC (Limited) | Vice Chancellor | IDA | 34 | 2023-02-10 | 2023-02-17 | 2023-03-01 | 2023-03-07 | 2023-03-19 | 2023-03-19 | 2023-12-31
SD 109C | National Consultant (Individual) Training Coordination Specialist (3.1) | PM | 23 | IC (Open) | Vice Chancellor | IDA | 74.89 | 2021-11-09 | 2022-01-19 | 2022-01-23 | 2022-01-25 | 2022-01-26 | 2022-01-26 | 2023-12-25
SD 110C | National Consultant (Individual) Financial Management Specialist (3.1) | PM | 22 | IC (Open) | Vice Chancellor | IDA | 69.25 | 2021-11-09 | 2021-12-28 | 2022-02-27 | 2022-02-28 | 2022-03-02 | 2022-03-02 | 2023-12-31
SD 111C | National Consultant (Individual) Accounts Specialist (3.1) | PM | 26 | IC (Limited) | Vice Chancellor | IDA | 70.56 | 2021-09-21 | 2021-10-07 | 2021-10-17 | 2021-10-21 | 2021-10-24 | 2021-10-24 | 2023-12-23
SD 119 | National Consultant (Individual) Strategic Plan Specialist - 2 (3.1) | PM | 6 | IC (Single Source) | Vice Chancellor | IDA | 13.98 | 2021-11-28 | 2021-12-12 | 2021-12-12 | 2022-01-04 | 2022-01-06 | 2022-01-09 | 2022-07-08
SD 124A | National Consultant (Individual) Junior Finance & Accounts Specialist (3.1) | PM | 31 | IC (Limited) | Vice Chancellor | IDA | 68.77 | 2021-05-02 | 2021-05-09 | 2021-05-19 | 2021-05-23 | 2021-05-27 | 2021-06-01 | 2023-12-31
SD 125 | National Consultant (Individual) Associate Network & IT Specialist (3.1) | PM | 21 | IC (Open) | Vice Chancellor | IDA | 48.79 | 2020-02-07 | 2022-03-09 | 2022-03-13 | 2022-03-16 | 2022-03-21 | 2022-03-21 | 2023-12-20
SD 126 | National Consultant (Individual) Self-Assesmentt Specialist (3.1) | PM | 27 | IC (Limited) | Vice Chancellor | IDA | 73.13 | 2021-09-14 | 2021-09-22 | 2021-09-30 | 2021-10-05 | 2021-10-06 | 2021-10-06 | 2023-12-31
SD 127 | National Consultant (Individual) Associate Strategic Plan Specialist-1 (3.1) | PM | 365 days | IC (Limited) | Vice Chancellor | IDA | 48.84 | 2021-11-24 | 2021-12-23 | 2022-01-27 | 2022-01-31 | 2022-02-07 | 2022-02-07 | 2023-12-31
SD 302 | Mid Term Satisfaction Survery (Beneficiary)-2 | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 66.81 | 2022-01-04 | 2022-02-10 | 2022-02-17 | 2022-02-23 | 2022-02-24 | 2022-03-01 | 2022-08-31
SD 303 | Audit Firm | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 24.54 | 2021-05-06 | 2021-06-15 | 2021-08-08 | 2021-08-16 | 2021-09-01 | 2021-09-01 | 2023-10-31
SD 403A | Survey and Studies (Effectiveness and Situation Assessment of Teacher's Training) | NS | Lumpsum | QCBS | Vice Chancellor | IDA | 24.22 | 2021-04-06 | 2021-06-15 | 2021-12-08 | 2021-12-09 | 2021-12-13 | 2021-01-01 | 2022-06-09
IDG/CP/ SD 601 | Planning, Design, Development, Deployment, Implementation, maintenance and Support Services of Integrated College Management Information System (CMIS) (SD-601) | NS | Lumpsum | QCBS | Vice Chancellor | GoB | 600 | 2022-03-07 | 2022-07-05 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-09-20 | 2023-12-31
SD 504 | Selection of Online Training Consulting Firm for Subjent Based Training | NS | Lumpsum | QCBS | Vice Chancellor | GoB | 100 | 2021-10-10 | 2022-02-27 | 2022-03-03 | 2022-08-15 | 2022-08-22 | 2022-09-01 | 2023-09-01
SD 603 | Design, Development, Implementation and Maintenance of Learning Management System (LMS) for National University, Bangladesh | NS | Lumpsum | QCBS | Vice Chancellor | GoB | 300 | 2022-03-08 | 2022-06-13 | 2022-08-31 | 2022-09-07 | 2022-09-14 | 2022-09-14 | 2023-12-31
IDG/CP/ SD 604A | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-08-15 | 2022-09-12 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-11-14 | 2023-05-13
IDG/CP/ SD 604B | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-08-25 | 2022-09-22 | 2022-10-13 | 2022-10-20 | 2022-10-27 | 2022-11-24 | 2023-05-23
IDG/CP/ SD 604C | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-09-01 | 2022-09-29 | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-12-01 | 2023-05-30
IDG/CP/ SD 604D | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-09-15 | 2022-10-13 | 2022-11-03 | 2022-11-10 | 2022-11-17 | 2022-12-15 | 2023-06-13
IDG/CP/ SD 604E | Internet Connectivity for IDG Colleges under CEDP | NS | Lumpsum | Single Source Selection | Vice Chancellor | GoB | 700 | 2022-09-30 | 2022-10-28 | 2022-11-18 | 2022-11-25 | 2022-12-02 | 2022-12-30 | 2023-06-28
SD 107B1 | National Consultant (Individual) Junior Procurement Specialist-2 (3.1) | PM | 17 | IC (Limited) | Vice Chancellor | IDA | 39.1 | 2022-09-01 | 2022-09-15 | 2022-10-06 | 2022-10-13 | 2022-10-20 | 2022-11-17 | 2023-12-31
SD 123 | National Consultant (Individual) Communication & Mobilisation Specialist (3.1) | PM | 17 | IC (Limited) | Vice Chancellor | IDA | 48.45 | 2022-11-01 | 2022-11-15 | 2022-12-06 | 2022-12-13 | 2022-12-20 | 2023-01-17 | 2023-12-31
SD 304 | LMS Content Development (Firm) | NS | Lumpsum | FBS | Vice Chancellor | GoB | 400 | 2022-09-01 | 2022-09-15 | 2022-10-15 | 2022-12-14 | 2022-12-21 | 2022-12-21 | 2023-12-31
SD 401 | DLI Verification Consultancy Firm for DLI-4 (2nd round) | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 70 | 2022-09-01 | 2022-09-15 | 2022-10-15 | 2022-12-14 | 2022-12-21 | 2022-12-21 | 2023-06-30
SD 403C | Survey and Studies (Effectiveness of the project) | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 70 | 2022-10-01 | 2022-10-15 | 2022-11-14 | 2023-01-13 | 2023-01-20 | 2023-01-20 | 2023-06-30
SD 404 | Survey and Studies (Tracer Study-2) (Follow up Tracer Study on Graduates of Tertiary- Level Colleges) | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 70 | 2022-09-01 | 2022-09-15 | 2022-10-15 | 2022-12-14 | 2022-12-21 | 2022-12-21 | 2023-06-30
SD 502 | Survey and Studies (Beneficiary-3: Endline Satisfaction Survey) | NS | Lumpsum | Single Source Selection | Vice Chancellor | IDA | 70 | 2022-10-01 | 2022-10-15 | 2022-11-14 | 2023-01-13 | 2023-01-20 | 2023-01-20 | 2023-06-30
Total Value of Services Procurement | [6 empty] | 6527.45
Formulas:
Issue of NOA = [Negotiation/Issue of RFP]+7
Contract Start date = [Signing of Contract]
Contract Start date = [Signing of Contract]+3
Negotiation/Issue of RFP = [Eval of EoIs]+60
Completion of Contract = [Contract Start date]+365
Completion of Contract = [Contract Start date]+360+15
Signing of Contract = [Issue of NOA]+7
Eval of EoIs = [Indicated Dates]+28